## Sheet1
Activity	Activity Description	DueDate	Activity Owner	Status	Comments
Functional Requirement Specification	A Text Document explaining the objectives of this project.	4/19/2018	Carlos Kassab	Done
Get Data For Analysis	Get initial data to create feasibility analysis	4/19/2018	Carlos Kassab	Done
Exploratory Data Analysis	This will be a histogram to know the data normalization	4/20/2018	Carlos Kassab	In progress
Dataset health status	– Getting metrics like total rows, columns, data types, zeros, and missing values	4/20/2018	Carlos Kassab	In progress
ETL Development	ETL to get final data for next analysis	4/20/2018	Carlos Kassab	Done	2018/04/19: In this case, there is not ETL needed, the dataset was downloaded from kaggle: https://www.kaggle.com/vivekchamp/bitcoin/data
Outliers Analysis	Analysis of variability in numeric variables, show it in charts and grids..	4/20/2018	Carlos Kassab	In progress
Variables frequency	Frequency of variable occurrence( frequence of shipments, etc. )	4/20/2018	Carlos Kassab	In progress
Modelling	Create the analytics model	4/25/2018	Carlos Kassab	Not Started
SQL View Development	For Training, Validation And Testing	NA	Carlos Kassab	Not Started	2018/04/19: No SQL view needed, everything is done inside the R script.
Model Selection	By using random parameters search algorithm, to find the right model to be used for this data.	4/25/2018	Carlos Kassab	Not Started
Model fine tunning.	After finding the right algorithm, find the right model parameters to be used.	4/25/2018	Carlos Kassab	Not Started
Chart Development	Final data chart development	4/25/2018	Carlos Kassab	Not Started
Data Validation	Run the analytics model at least 2 weeks daily in order to see its behavior.	NA	Carlos Kassab	Not Started